## PMS
[8 empty] | PMS | [6 empty] | plan Weight |  |  | plan Progress |  |  | Actual Weight |  |  | Actual Progress
coding | Project | A | B | C | D | E | CC | DESCRIPTION | UNIT | WBS | W.F | WEIGHT | START | Finished | Last | This | Total | Last | This | Total | Last | This | Total | Last | This | Total
| Ethylene Plant Expansion - Civil , Steel Structure & Funrnaces Works | [9 empty] | 100% | [12 empty] | 62.5% | 0% | 63.03%
|  | 1.START | [8 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
|  |  | 1.start | [7 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
|  |  |  | start project | [6 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
[5 empty] | 1.start project | [5 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
[6 empty] | start project |  |  |  |  | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
[7 empty] | 601.1.1.1.1.01.01 | Cracking Furnaces Erection (OLF1) |  | 50% | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
[7 empty] | 601.1.1.1.1.01.02 | Cracking Furnaces Erection (OLF2) |  | 50% | 0% | 0 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
|  | 2.Mobilization | [8 empty] | 1% | 1 | [8 empty] | 0 | 0 | 0 | 100% | 0% | 100%
|  |  | 2.Mobilization | [7 empty] | 1% | 1 | [8 empty] | 1 | 0 | 1 | 100% | 0% | 100%
|  |  |  | 1.Mobilization | [6 empty] | 1% | 1 | [8 empty] | 1 | 0 | 1 | 100% | 0% | 100%
[5 empty] | 1.Mobilization project | [5 empty] | 1% | 1 | [8 empty] | 1 | 0 | 1 | 100% | 0% | 100%
[6 empty] | Mobilization project |  |  |  |  | 1% | 1 | [8 empty] | 1 | 0 | 1 | 100% | 0% | 100%
[7 empty] | 601.2.1.1.1.01.01 | Cracking Furnaces Erection (OLF1) |  | 50% | 0.5% | 0.5 | [8 empty] | 0.5 | 0 | 0.5 | 100% | 0% | 100%
[7 empty] | 601.2.1.1.1.01.02 | Cracking Furnaces Erection (OLF2) |  | 50% | 0.5% | 0.5 | [8 empty] | 0.5 | 0 | 0.5 | 100% | 0% | 100%
|  | 3.Cracking Furnaces Erection (OLF1) | [8 empty] | 48.57% | 1268662.45 | [8 empty] | 906449.4389 | 0 | 906449.4389 | 67.38% | 0% | 67.38%
|  |  | 1.F110 | [7 empty] | 42.82% | 1186857.45 | [8 empty] | 906449.4389 | 0 | 906449.4389 | 76.43% | 0% | 76.43%
|  |  |  | 1.Furnaces Steel Structure (Plate & Steel) | [6 empty] | 19.75% | 432867.5 | [8 empty] | 415197.5 | 0 | 415197.5 | 86.52% | 0% | 86.52%
[5 empty] | 01.Radiant Plate Sections | [5 empty] | 4.894% | 110000 | [8 empty] | 110000 | 0 | 110000 | 100% | 0% | 100%
[6 empty] | 1A Radiant Floor Panels |  |  |  |  | 0.3519% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0101 | Material Handling |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0102 | Installation |  | 50% | 0.1759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0103 | Leveling & Plumbness |  | 15% | 0.05278% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0104 | Full Bolt & Tightening |  | 20% | 0.07038% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0105 | Touch up |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0106 | Certificate |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[6 empty] | 1B Radiant Side Wall Panels Axis B+F(Out side) |  |  |  |  | 1.742% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0201 | Material Handling | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0202 | Chipping&Padding | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0203 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.8711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0204 | Bolting | KG | 10% | 0.1742% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0205 | Aligenment | KG | 15% | 0.2613% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0206 | Grouting | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0207 | Punch Removing | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0208 | Finall Inspection | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[6 empty] | 1C Radiant Side Wall Panels Axis C+E(Inside) |  |  |  |  | 1.695% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0301 | Material Handling | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0302 | Chipping&Padding | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0303 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.8477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0304 | Bolting | KG | 10% | 0.1695% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0305 | Aligenment | KG | 15% | 0.2543% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0306 | Grouting | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0307 | Punch Removing | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0308 | Finall Inspection | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[6 empty] | 1D Radiant End Wall Panels |  |  |  |  | 0.4198% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0401 | Material Handling |  | 5% | 0.02099% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0402 | Installation |  | 50% | 0.2099% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0403 | Leveling & Plumbness |  | 15% | 0.06297% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0404 | Full Bolt & Tightening |  | 20% | 0.08397% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0405 | Touch up |  | 5% | 0.02099% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0406 | Certificate |  | 5% | 0.02099% | 10000 | [8 empty] | 10000 | 0 | 10000 | 100% | 0% | 100%
[6 empty] | 1E Radiant Roof Panels |  |  |  |  | 0.3654% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0501 | Material Handling |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0502 | Installation |  | 50% | 0.1827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0503 | Leveling & Plumbness |  | 15% | 0.05481% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0504 | Full Bolt & Tightening |  | 20% | 0.07308% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0505 | Touch up |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0506 | Certificate |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[6 empty] | 1F Radiant Roof Shadow Box |  |  |  |  | 0.1059% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0601 | Material Handling |  | 5% | 0.005295% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0602 | Installation |  | 50% | 0.05295% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0603 | Leveling & Plumbness |  | 15% | 0.01588% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0604 | Full Bolt & Tightening |  | 20% | 0.02118% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0605 | Touch up |  | 5% | 0.005295% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0606 | Certificate |  | 5% | 0.005295% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
[6 empty] | 1G Radiant Transition Roof To Convection |  |  |  |  | 0.2137% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0701 | Material Handling |  | 5% | 0.01069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.1.0702 | Installation |  | 50% | 0.1069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0703 | Leveling & Plumbness |  | 15% | 0.03206% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0704 | Full Bolt & Tightening |  | 20% | 0.04274% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0705 | Touch up |  | 5% | 0.01069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.1.0706 | Certificate |  | 5% | 0.01069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[5 empty] | 02.Radiant Steel Sections | [5 empty] | 4.124% | 102421 | [8 empty] | 102421 | 0 | 102421 | 100% | 0% | 100%
[6 empty] | 2A1 Columns Steel Structure |  |  |  |  | 1.617% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0101 | Material Handling | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0102 | Chipping&Padding | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.2.0103 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.8085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0104 | Bolting | KG | 10% | 0.1617% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0105 | Aligenment | KG | 15% | 0.2425% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0106 | Grouting | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0107 | Punch Removing | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0108 | Finall Inspection | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[6 empty] | 2A2 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0201 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.2.0202 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0203 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0204 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0205 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0206 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A3 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0301 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.2.0302 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0303 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0304 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0305 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0306 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A4 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0401 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.2.0402 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0403 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0404 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0405 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0406 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A5 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0501 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.2.0502 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0503 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0504 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0505 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0506 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2B Railing (Handrail) For Radiant Platforms |  |  |  |  | 0.4616% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0601 | Material Handling |  | 5% | 0.02308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
02.Lader & Handrail | [6 empty] | 601.3.1.1.2.0602 | Installation |  | 50% | 0.2308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0603 | Leveling & Plumbness |  | 15% | 0.06924% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0604 | Full Bolt & Tightening |  | 20% | 0.09232% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0605 | Touch up |  | 5% | 0.02308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0606 | Certificate |  | 5% | 0.02308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[6 empty] | 2C Ladders For Radiant Platforms |  |  |  |  | 0.0605% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0701 | Material Handling |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
02.Lader & Handrail | [6 empty] | 601.3.1.1.2.0702 | Installation |  | 50% | 0.03025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0703 | Leveling & Plumbness |  | 15% | 0.009075% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0704 | Full Bolt & Tightening |  | 20% | 0.0121% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0705 | Touch up |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0706 | Certificate |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[6 empty] | 2D Grating For Radiant Platforms |  |  |  |  | 0.417% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0801 | Material Handling | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
03.Grating | [6 empty] | 601.3.1.1.2.0802 | installation | KG | 65% | 0.2711% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0803 | Clamping & Tightening | KG | 20% | 0.0834% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0804 | Touch up & Cleaning | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.2.0805 | Certificate | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[5 empty] | 03.Convection, Header Box Convection Breeching Plate Sections | [5 empty] | 2.522% | 57000 | [8 empty] | 44000 | 0 | 44000 | 77.54% | 0% | 77.54%
[6 empty] | 3A Convection Floor Panels |  |  |  |  | 0.1812% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0101 | Material Handling |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.3.0102 | Installation |  | 50% | 0.09058% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0103 | Leveling & Plumbness |  | 15% | 0.02717% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0104 | Full Bolt & Tightening |  | 20% | 0.03623% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0105 | Touch up |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0106 | Certificate |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[6 empty] | 3B Convection Side Wall (Inside) |  |  |  |  | 1.039% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0201 | Material Handling |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.3.0202 | Installation |  | 50% | 0.5197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0203 | Leveling & Plumbness |  | 15% | 0.1559% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0204 | Full Bolt & Tightening |  | 20% | 0.2079% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0205 | Touch up |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0206 | Certificate |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[6 empty] | 3C Convection Side Wall (Outside) |  |  |  |  | 0.735% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0301 | Material Handling |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.3.0302 | Installation |  | 50% | 0.3675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0303 | Leveling & Plumbness |  | 15% | 0.1103% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0304 | Full Bolt & Tightening |  | 20% | 0.147% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0305 | Touch up |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.3.0306 | Certificate |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[6 empty] | 3D Header box |  |  |  |  | 0.3526% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0401 | Material Handling |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.3.0402 | Installation |  | 50% | 0.1763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0403 | Leveling & Plumbness |  | 15% | 0.05289% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0404 | Full Bolt & Tightening |  | 20% | 0.07052% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0405 | Touch up |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0406 | Certificate |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3E Convection Breeching |  |  |  |  | 0.2139% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0501 | Material Handling |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.3.0502 | Installation |  | 50% | 0.1069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0503 | Leveling & Plumbness |  | 15% | 0.03208% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0504 | Full Bolt & Tightening |  | 20% | 0.04277% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0505 | Touch up |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.3.0506 | Certificate |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 04.Flue Gas Duct & Stack Plate Section | [5 empty] | 0.09627% | 2510 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3F Flue Gas Duc |  |  |  |  | 0.06198% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0101 | Material Handling |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.4.0102 | Installation |  | 50% | 0.03099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0103 | Leveling & Plumbness |  | 15% | 0.009297% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0104 | Full Bolt & Tightening |  | 20% | 0.0124% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0105 | Touch up |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0106 | Certificate |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3G Stack |  |  |  |  | 0.03429% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0201 | Material Handling |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.4.0202 | Installation |  | 50% | 0.01715% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0203 | Leveling & Plumbness |  | 15% | 0.005143% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0204 | Full Bolt & Tightening |  | 20% | 0.006858% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0205 | Touch up |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.4.0206 | Certificate |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 05.Convection & Upper Steel Section | [5 empty] | 6.113% | 158776.5 | [8 empty] | 158776.5 | 0 | 158776.5 | 100% | 0% | 100%
[6 empty] | 4A1 Platform |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0101 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.5.0102 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0103 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0104 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0105 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0106 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[6 empty] | 4A2 Columns And Steel Structure |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0201 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.5.0202 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0203 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0204 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0205 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0206 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[6 empty] | 4A3 Columns And Steel Structure |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0301 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.5.0302 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0303 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0304 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0305 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0306 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[6 empty] | 4B Railing (Handrail) For Convection & Upper Section Platforms |  |  |  |  | 0.2157% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0401 | Material Handling |  | 5% | 0.01078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
02.Lader & Handrail | [6 empty] | 601.3.1.1.5.0402 | Installation |  | 50% | 0.1078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0403 | Leveling & Plumbness |  | 15% | 0.03235% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0404 | Full Bolt & Tightening |  | 20% | 0.04314% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0405 | Touch up |  | 5% | 0.01078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0406 | Certificate |  | 5% | 0.01078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[6 empty] | 4C Ladders For Convection & Upper Section Platforms |  |  |  |  | 0.06037% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0501 | Material Handling |  | 5% | 0.003018% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
02.Lader & Handrail | [6 empty] | 601.3.1.1.5.0502 | Installation |  | 50% | 0.03019% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0503 | Leveling & Plumbness |  | 15% | 0.009056% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0504 | Full Bolt & Tightening |  | 20% | 0.01207% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0505 | Touch up |  | 5% | 0.003018% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0506 | Certificate |  | 5% | 0.003018% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[6 empty] | 4D Grating For Convection & Upper Section Platforms |  |  |  |  | 0.4276% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0601 | Material Handling | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
03.Grating | [6 empty] | 601.3.1.1.5.0602 | installation | KG | 65% | 0.2779% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0603 | Clamping & Tightening | KG | 20% | 0.08551% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0604 | Touch up & Cleaning | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
[7 empty] | 601.3.1.1.5.0605 | Certificate | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 24780.5 | 0 | 24780.5 | 100% | 0% | 100%
[5 empty] | 06.Other Accessories | [5 empty] | 2% | 2160 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Peep Doors |  |  |  |  | 1% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.6.0101 | Installation | KG | 50% | 0.5% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.6.0102 | Tightening | KG | 25% | 0.25% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.6.0103 | Certificate | KG | 25% | 0.25% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Accessories Doors(Z-1110) |  |  |  |  | 1% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
01.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.3.1.1.6.0201 | Installation | KG | 50% | 0.5% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.6.0202 | Tightening | KG | 25% | 0.25% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.1.6.0203 | Certificate | KG | 25% | 0.25% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 2.Furnace Coil System | [6 empty] | 4.5% | 189708.2 | [8 empty] | 10418.0089 | 0 | 10418.0089 | 36.11% | 0% | 36.11%
[5 empty] | 07.Radiant Coils & Accessories | [5 empty] | 2% | 40200 | [8 empty] | 22110 | 0 | 22110 | 55% | 0% | 55%
[6 empty] | Radiant Coils (Inlet Coil & OutlentCoil) |  |  |  |  | 2% | 40200 | [8 empty] | 22110 | 0 | 22110 | 55% | 0% | 55%
[7 empty] | 601.3.1.2.1.0101 | Material Handling | KG | 5% | 0.1% | 40200 | [8 empty] | 40200 | 0 | 40200 | 100% | 0% | 100%
05.Furnace Coil System | [6 empty] | 601.3.1.2.1.0102 | Erection | KG | 50% | 1% | 40200 | [8 empty] | 40200 | 0 | 40200 | 100% | 0% | 100%
[7 empty] | 601.3.1.2.1.0103 | Aligenment/Leveling | KG | 20% | 0.4% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.1.0104 | Full Bolting/Welding | KG | 15% | 0.3% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.1.0106 | Punch Removing | KG | 5% | 0.1% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.1.0107 | Certificate | KG | 5% | 0.1% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 08.Convection Coils & Accessories | [5 empty] | 1.7% | 144440.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Economiser (ECO) |  |  |  |  | 0.2% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0101 | Material Handling | NO. | 10% | 0.02% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0102 | Installation | NO. | 60% | 0.12% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0103 | Fixing & tightening | NO. | 15% | 0.03% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0104 | Setting & Alignment | NO. | 10% | 0.02% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0105 | Certificate | NO. | 5% | 0.01% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Feed Preheater (FPH) |  |  |  |  | 0.21% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0201 | Material Handling | NO. | 10% | 0.021% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0202 | Installation | NO. | 60% | 0.126% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0203 | Fixing & tightening | NO. | 15% | 0.0315% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0204 | Setting & Alignment | NO. | 10% | 0.021% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0205 | Certificate | NO. | 5% | 0.0105% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Pressure Steam Superheater One (HPSSH-I) |  |  |  |  | 0.1% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0301 | Material Handling | NO. | 10% | 0.01% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0302 | Installation | NO. | 60% | 0.06% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0303 | Fixing & tightening | NO. | 15% | 0.015% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0304 | Setting & Alignment | NO. | 10% | 0.01% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0305 | Certificate | NO. | 5% | 0.005% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Pressure Steam Superheater One (HPSSH-II) |  |  |  |  | 0.09% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0401 | Material Handling | NO. | 10% | 0.009% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0402 | Installation | NO. | 60% | 0.054% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0403 | Fixing & tightening | NO. | 15% | 0.0135% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0404 | Setting & Alignment | NO. | 10% | 0.009% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0405 | Certificate | NO. | 5% | 0.0045% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Temperature Coil One (HTC-I) |  |  |  |  | 0.25% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0501 | Material Handling | NO. | 10% | 0.025% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0502 | Installation | NO. | 60% | 0.15% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0503 | Fixing & tightening | NO. | 15% | 0.0375% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0504 | Setting & Alignment | NO. | 10% | 0.025% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0505 | Certificate | NO. | 5% | 0.0125% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Temperature Coil One (HTC-II) |  |  |  |  | 0.2% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0601 | Material Handling | NO. | 10% | 0.02% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0602 | Installation | NO. | 60% | 0.12% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0603 | Fixing & tightening | NO. | 15% | 0.03% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0604 | Setting & Alignment | NO. | 10% | 0.02% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0605 | Certificate | NO. | 5% | 0.01% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | HT Crossover (HTX) |  |  |  |  | 0.09% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0701 | Material Handling | NO. | 10% | 0.009% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0702 | Installation | NO. | 60% | 0.054% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0703 | Fixing & tightening | NO. | 15% | 0.0135% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0704 | Setting & Alignment | NO. | 10% | 0.009% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0705 | Certificate | NO. | 5% | 0.0045% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | LT Crossover B(LTX-B) |  |  |  |  | 0.09% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0801 | Material Handling | NO. | 10% | 0.009% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0802 | Installation | NO. | 60% | 0.054% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0803 | Fixing & tightening | NO. | 15% | 0.0135% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0804 | Setting & Alignment | NO. | 10% | 0.009% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0805 | Certificate | NO. | 5% | 0.0045% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | LT Crossover T(LTX-T) |  |  |  |  | 0.06% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0901 | Material Handling | NO. | 10% | 0.006% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.0902 | Installation | NO. | 60% | 0.036% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0903 | Fixing & tightening | NO. | 15% | 0.009% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0904 | Setting & Alignment | NO. | 10% | 0.006% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.0905 | Certificate | NO. | 5% | 0.003% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Venture For X-Over System |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1001 | Material Handling | NO. | 10% | 0.01% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.1002 | Installation | NO. | 60% | 0.06% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1003 | Fixing & tightening | NO. | 15% | 0.015% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1004 | Setting & Alignment | NO. | 10% | 0.01% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1005 | Certificate | NO. | 5% | 0.005% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Comsockets |  |  |  |  | 0.08% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1101 | Material Handling | NO. | 10% | 0.008% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.1102 | Installation | NO. | 60% | 0.048% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1103 | Fixing & tightening | NO. | 15% | 0.012% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1104 | Setting & Alignment | NO. | 10% | 0.008% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1105 | Certificate | NO. | 5% | 0.004% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Brackets |  |  |  |  | 0.15% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1201 | Material Handling | NO. | 10% | 0.015% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.1202 | Installation | NO. | 60% | 0.09% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1203 | Fixing & tightening | NO. | 15% | 0.0225% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1204 | Setting & Alignment | NO. | 10% | 0.015% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1205 | Certificate | NO. | 5% | 0.0075% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Common Part |  |  |  |  | 0.08% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1301 | Material Handling | NO. | 10% | 0.008% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
05.Furnace Coil System | [6 empty] | 601.3.1.2.2.1302 | Installation | NO. | 60% | 0.048% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1303 | Fixing & tightening | NO. | 15% | 0.012% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1304 | Setting & Alignment | NO. | 10% | 0.008% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.2.1305 | Certificate | NO. | 5% | 0.004% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 09.Spring Support | [5 empty] | 0.8% | 5068 | [8 empty] | 3326.3 | 0 | 3326.3 | 65.63% | 0% | 65.63%
[6 empty] | Content Spring Support & HangerTie-Roads |  |  |  |  | 0.8% | 5068 | [8 empty] | 3326.3 | 0 | 3326.3 | 65.63% | 0% | 65.63%
[7 empty] | 601.3.1.2.3.0101 | Material Handling |  | 5% | 0.04% | 5068 | [8 empty] | 5068 | 0 | 5068 | 100% | 0% | 100%
06.Spring Support | [6 empty] | 601.3.1.2.3.0102 | Erection |  | 55% | 0.44% | 5068 | [8 empty] | 5068 | 0 | 5068 | 100% | 0% | 100%
[7 empty] | 601.3.1.2.3.0103 | Fixing & tightening |  | 25% | 0.2% | 5068 | [8 empty] | 1142 | 0 | 1142 | 22.53% | 0% | 22.53%
[7 empty] | 601.3.1.2.3.0104 | Punch Removing |  | 10% | 0.08% | 5068 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.2.3.0105 | Certificate |  | 5% | 0.04% | 5068 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 3.Furnace Equipment | [6 empty] | 5.5% | 230164.2 | [8 empty] | 148070.52 | 0 | 148070.52 | 58.64% | 0% | 58.64%
[5 empty] | 10.FIX Equipment | [5 empty] | 5.5% | 230164.2 | [8 empty] | 148070.52 | 0 | 148070.52 | 58.64% | 0% | 58.64%
[6 empty] | Bottom Burners (F1110) |  |  |  |  | 0.45% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0101 | Material Handling | NO. | 10% | 0.045% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0102 | Installation | NO. | 60% | 0.27% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0103 | Fixing & tightening | NO. | 15% | 0.0675% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0104 | Setting & Alignment | NO. | 10% | 0.045% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0105 | Certificate | NO. | 5% | 0.0225% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Side Wall Burners( F1111) |  |  |  |  | 0.45% | 14628.6 | [8 empty] | 11540.52 | 0 | 11540.52 | 78.89% | 0% | 78.89%
[7 empty] | 601.3.1.3.1.0201 | Material Handling | NO. | 10% | 0.045% | 14628.6 | [8 empty] | 14628.6 | 0 | 14628.6 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0202 | Installation | NO. | 60% | 0.27% | 14628.6 | [8 empty] | 14628.6 | 0 | 14628.6 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0203 | Fixing & tightening | NO. | 15% | 0.0675% | 14628.6 | [8 empty] | 8670 | 0 | 8670 | 59.27% | 0% | 59.27%
[7 empty] | 601.3.1.3.1.0204 | Setting & Alignment | NO. | 10% | 0.045% | 14628.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0205 | Certificate | NO. | 5% | 0.0225% | 14628.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Primery TLE (E-110 A) |  |  |  |  | 0.49% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0301 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0302 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0303 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0304 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0305 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[6 empty] | Primery TLE (E-110 B) |  |  |  |  | 0.49% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0401 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0402 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0403 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0404 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0405 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[6 empty] | Primery TLE (E-110 C) |  |  |  |  | 0.49% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0501 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0502 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0503 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0504 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0505 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[6 empty] | Secondary TLE (E-1120) |  |  |  |  | 0.6% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0601 | Material Handling | NO. | 10% | 0.06% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0602 | Installation | NO. | 60% | 0.36% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0603 | Fixing & tightening | NO. | 15% | 0.09% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0604 | Setting & Alignment | NO. | 10% | 0.06% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0605 | Certificate | NO. | 5% | 0.03% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[6 empty] | Tertiary TLE (E-1130) |  |  |  |  | 0.8% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0701 | Material Handling | NO. | 10% | 0.08% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0702 | Installation | NO. | 60% | 0.48% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0703 | Fixing & tightening | NO. | 15% | 0.12% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0704 | Setting & Alignment | NO. | 10% | 0.08% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.3.1.3.1.0705 | Certificate | NO. | 5% | 0.04% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[6 empty] | Decocke Drum (D-11110)B |  |  |  |  | 0.28% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0801 | Material Handling | NO. | 10% | 0.028% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0802 | Installation | NO. | 60% | 0.168% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0803 | Fixing & tightening | NO. | 15% | 0.042% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0804 | Setting & Alignment | NO. | 10% | 0.028% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0805 | Certificate | NO. | 5% | 0.014% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | VHPS Steam Drum (D-1110) |  |  |  |  | 0.6% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0901 | Material Handling | NO. | 10% | 0.06% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.0902 | Installation | NO. | 60% | 0.36% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0903 | Fixing & tightening | NO. | 15% | 0.09% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0904 | Setting & Alignment | NO. | 10% | 0.06% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.0905 | Certificate | NO. | 5% | 0.03% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | VHPS Steam Silencer (X-1110) |  |  |  |  | 0.2% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1001 | Material Handling | NO. | 10% | 0.02% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.1002 | Installation | NO. | 60% | 0.12% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1003 | Fixing & tightening | NO. | 15% | 0.03% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1004 | Setting & Alignment | NO. | 10% | 0.02% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1005 | Certificate | NO. | 5% | 0.01% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Decocke Air Silencer (X-1120) |  |  |  |  | 0.25% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1101 | Material Handling | NO. | 10% | 0.025% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.1102 | Installation | NO. | 60% | 0.15% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1103 | Fixing & tightening | NO. | 15% | 0.0375% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1104 | Setting & Alignment | NO. | 10% | 0.025% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1105 | Certificate | NO. | 5% | 0.0125% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Induct Draft Fan (C-1110 & M1110) |  |  |  |  | 0.4% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1201 | Material Handling | NO. | 10% | 0.04% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
07.Fix Equipment | [6 empty] | 601.3.1.3.1.1202 | Installation | NO. | 60% | 0.24% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1203 | Fixing & tightening | NO. | 15% | 0.06% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1204 | Setting & Alignment | NO. | 10% | 0.04% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.3.1.1205 | Certificate | NO. | 5% | 0.02% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 4.Refractory Lining & Insulating Firebricks | [6 empty] | 11.82% | 333983.55 | [8 empty] | 332763.41 | 0 | 332763.41 | 91.28% | 0% | 91.28%
[5 empty] | 11.Refractory Lining & Insulating Firebricks | [5 empty] | 11.82% | 333983.55 | [8 empty] | 332763.41 | 0 | 332763.41 | 91.28% | 0% | 91.28%
[6 empty] | Radiant Floor |  |  |  |  | 1% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0101 | Material Handling |  | 10% | 0.1% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0102 | Preparatoin |  | 5% | 0.05% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0103 | Installation |  | 60% | 0.6% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0104 | Completion Work |  | 15% | 0.15% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0105 | Punch Removing & Cleaning |  | 5% | 0.05% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0106 | Certificate |  | 5% | 0.05% | 20576 | [8 empty] | 20576 | 0 | 20576 | 100% | 0% | 100%
[6 empty] | Radiant Side Wall And South End Wall |  |  |  |  | 3.515% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0201 | Material Handling |  | 10% | 0.3515% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0202 | Preparatoin |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0203 | Installation |  | 60% | 2.109% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0204 | Completion Work |  | 15% | 0.5272% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0205 | Punch Removing & Cleaning |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0206 | Certificate |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[6 empty] | Radiant North End Wall |  |  |  |  | 0.6% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 95% | 0% | 95%
[7 empty] | 601.3.1.4.1.0301 | Material Handling |  | 10% | 0.06% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0302 | Preparatoin |  | 5% | 0.03% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0303 | Installation |  | 60% | 0.36% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0304 | Completion Work |  | 15% | 0.09% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0305 | Punch Removing & Cleaning |  | 5% | 0.03% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0306 | Certificate |  | 5% | 0.03% | 20385.38 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Radiant Roof And shadow Box |  |  |  |  | 0.35% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0401 | Material Handling |  | 10% | 0.035% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0402 | Preparatoin |  | 5% | 0.0175% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0403 | Installation |  | 60% | 0.21% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0404 | Completion Work |  | 15% | 0.0525% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0405 | Punch Removing & Cleaning |  | 5% | 0.0175% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0406 | Certificate |  | 5% | 0.0175% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[6 empty] | Cross Over Floor |  |  |  |  | 0.5% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0501 | Material Handling |  | 10% | 0.05% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0502 | Preparatoin |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0503 | Installation |  | 60% | 0.3% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0504 | Completion Work |  | 15% | 0.075% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0505 | Punch Removing & Cleaning |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0506 | Certificate |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[6 empty] | Cross Over Side Wall And South End Wall |  |  |  |  | 1.22% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0601 | Material Handling |  | 10% | 0.122% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0602 | Preparatoin |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0603 | Installation |  | 60% | 0.732% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0604 | Completion Work |  | 15% | 0.183% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0605 | Punch Removing & Cleaning |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0606 | Certificate |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[6 empty] | Cross Over Roof |  |  |  |  | 0.8% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0701 | Material Handling |  | 10% | 0.08% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0702 | Preparatoin |  | 5% | 0.04% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0703 | Installation |  | 60% | 0.48% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0704 | Completion Work |  | 15% | 0.12% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0705 | Punch Removing & Cleaning |  | 5% | 0.04% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0706 | Certificate |  | 5% | 0.04% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[6 empty] | Convection Side Wall |  |  |  |  | 1.5% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0801 | Material Handling |  | 10% | 0.15% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0802 | Preparatoin |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0803 | Installation |  | 60% | 0.9% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0804 | Completion Work |  | 15% | 0.225% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0805 | Punch Removing & Cleaning |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.0806 | Certificate |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[6 empty] | Header Box |  |  |  |  | 1% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.4.1.0901 | Material Handling |  | 10% | 0.1% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.4.1.0902 | Preparatoin |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.0903 | Installation |  | 60% | 0.6% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.4.1.0904 | Completion Work |  | 15% | 0.15% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.4.1.0905 | Punch Removing & Cleaning |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.4.1.0906 | Certificate |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | breeching |  |  |  |  | 0.83% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1001 | Material Handling |  | 10% | 0.083% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1002 | Preparatoin |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.1003 | Installation |  | 60% | 0.498% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1004 | Completion Work |  | 15% | 0.1245% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1005 | Punch Removing & Cleaning |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1006 | Certificate |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[6 empty] | Shadow Box |  |  |  |  | 0.5% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1101 | Material Handling |  | 10% | 0.05% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1102 | Preparatoin |  | 5% | 0.025% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
08.Refractory Lining & Insulating Firebricks | [6 empty] | 601.3.1.4.1.1103 | Installation |  | 60% | 0.3% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1104 | Completion Work |  | 15% | 0.075% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1105 | Punch Removing & Cleaning |  | 5% | 0.025% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
[7 empty] | 601.3.1.4.1.1106 | Certificate |  | 5% | 0.025% | 5043.25 | [8 empty] | 5043.25 | 0 | 5043.25 | 100% | 0% | 100%
|  |  |  | 5.Protrusion Seals | [6 empty] | 1.25% | 134 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 12.Protrusion Seals | [5 empty] | 1.25% | 134 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Multi Tube Bellow (End Location) |  |  |  |  | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0101 | Completion Work | - | 100% | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Multi Tube Bellow (Intermediate Location) |  |  |  |  | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0201 | Completion Work | - | 100% | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Spring Joint (Hanger Tube Through Arch ) |  |  |  |  | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0301 | Completion Work | - | 100% | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Spring Joint (Guide Tube Through Floor ) |  |  |  |  | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0401 | Completion Work | - | 100% | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | CRF Rope (Outlet Tube) |  |  |  |  | 0.25% | 96 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0501 | Completion Work | - | 100% | 0.25% | 96 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Certification |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.1.5.1.0601 | Completion Work | - | 100% | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 2.PipeRack A1 (OLFINE 1) | [7 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 6.PipeRack A1 (OLFINE 1) | [6 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 13.PipeRack A1 (OLFINE 1) | [5 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 5A+5C Stair House |  |  |  |  | 1.5% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0101 | Material Handling | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0102 | Chipping&Padding | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
04.PipeRack A1 (OLFINE 1) | [6 empty] | 601.3.2.1.1.0103 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.75% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0104 | Bolting | KG | 10% | 0.15% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0105 | Aligenment | KG | 15% | 0.225% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0106 | Grouting | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0107 | Punch Removing | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0108 | Finall Inspection | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 5B+5D Handrial Stair |  |  |  |  | 0.25% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0201 | Material Handling |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
04.PipeRack A1 (OLFINE 1) | [6 empty] | 601.3.2.1.1.0202 | Installation |  | 50% | 0.125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0203 | Leveling & Plumbness |  | 15% | 0.0375% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0204 | Full Bolt & Tightening |  | 20% | 0.05% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0205 | Touch up |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0206 | Certificate |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 5B+5D Handrial Stair |  |  |  |  | 0.25% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0301 | Material Handling | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
04.PipeRack A1 (OLFINE 1) | [6 empty] | 601.3.2.1.1.0302 | installation | KG | 65% | 0.1625% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0303 | Clamping & Tightening | KG | 20% | 0.05% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0304 | Touch up & Cleaning | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.2.1.1.0305 | Certificate | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 3.Inlet & Outlet Piping | [7 empty] | 3% | 1800 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 7.Piping From Inlet Header To Furnace | [6 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 14.grinding & Fitup & Welding | [5 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Workshop |  |  |  |  | 0.5% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0101 | Material Handling | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
09.Inlet & Outlet Piping | [6 empty] | 601.3.3.1.1.0102 | Fitup | KG | 30% | 0.15% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
10.Inlet & Outlet Piping | [6 empty] | 601.3.3.1.1.0103 | Welding | KG | 35% | 0.175% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0104 | NDT & PWHT | KG | 15% | 0.075% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0106 | Reinstatement | KG | 10% | 0.05% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0107 | Certificate | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Location |  |  |  |  | 1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0201 | Material Handling | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
09.Inlet & Outlet Piping | [6 empty] | 601.3.3.1.1.0202 | Fitup | KG | 30% | 0.3% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
10.Inlet & Outlet Piping | [6 empty] | 601.3.3.1.1.0203 | Welding | KG | 35% | 0.35% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0204 | NDT & PWHT | KG | 15% | 0.15% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0206 | Reinstatement | KG | 10% | 0.1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.1.1.0207 | Certificate | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 8.Piping From Inlet Header To Furnace | [6 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 15.grinding & Fitup & Welding | [5 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Workshop |  |  |  |  | 0.5% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0101 | Material Handling | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
09.Inlet & Outlet Piping | [6 empty] | 601.3.3.2.1.0102 | Fitup | KG | 30% | 0.15% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
10.Inlet & Outlet Piping | [6 empty] | 601.3.3.2.1.0103 | Welding | KG | 35% | 0.175% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0104 | NDT & PWHT | KG | 15% | 0.075% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0106 | Reinstatement | KG | 10% | 0.05% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0107 | Certificate | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Location |  |  |  |  | 1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0201 | Material Handling | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
09.Inlet & Outlet Piping | [6 empty] | 601.3.3.2.1.0202 | Fitup | KG | 30% | 0.3% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
10.Inlet & Outlet Piping | [6 empty] | 601.3.3.2.1.0203 | Welding | KG | 35% | 0.35% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0204 | NDT & PWHT | KG | 15% | 0.15% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0206 | Reinstatement | KG | 10% | 0.1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.3.2.1.0207 | Certificate | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 4.Delivery of MC Book | [7 empty] | 0.75% | 5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 9.F-110 | [6 empty] | 0.695% | 4.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 16.Furnace & Refractory | [5 empty] | 0.695% | 4.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Steel Structure (Plate & Steel) |  |  |  |  | 0.245% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.1.1.0101 | Completion Work | - | 100% | 0.245% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Coil System |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.1.1.0201 | Completion Work | - | 100% | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Coil Equipment |  |  |  |  | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.1.1.0301 | Completion Work | - | 100% | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Refractory Lining & Insulating Firebricks |  |  |  |  | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.1.1.0401 | Completion Work | - | 100% | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Protrusion Seals |  |  |  |  | 0.05% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.1.1.0501 | Completion Work | - | 100% | 0.05% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 9.PipeRack A1 (OLFINE 1) | [6 empty] | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 17.Stair House For F-111 | [5 empty] | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Stair House For F-112 |  |  |  |  | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.3.4.2.1.0101 | Completion Work | - | 100% | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  | 4.Cracking Furnaces Erection (OLF2) | [8 empty] | 48.57% | 1268662.45 | [8 empty] | 846794.3679 | 0 | 608247.3677 | 59.26% | 0% | 60.35%
|  |  | 1.F110 | [7 empty] | 42.81% | 1186857.45 | [8 empty] | 846794.3679 | 0 | 608247.3677 | 67.22% | 0% | 68.26%
|  |  |  | 1.Furnaces Steel Structure (Plate & Steel) | [6 empty] | 19.75% | 432867.5 | [8 empty] | 411719.45 | 0 | 411719.45 | 82.12% | 0% | 82.35%
[5 empty] | 01.Radiant Plate Sections | [5 empty] | 4.894% | 110000 | [8 empty] | 109000 | 0 | 109000 | 97.28% | 0% | 97.83%
[6 empty] | 1A Radiant Floor Panels |  |  |  |  | 0.3519% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0101 | Material Handling |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0102 | Installation |  | 50% | 0.1759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0103 | Leveling & Plumbness |  | 15% | 0.05278% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0104 | Full Bolt & Tightening |  | 20% | 0.07038% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0105 | Touch up |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0106 | Certificate |  | 5% | 0.01759% | 9000 | [8 empty] | 9000 | 0 | 9000 | 100% | 0% | 100%
[6 empty] | 1B Radiant Side Wall Panels Axis B+F(Out side) |  |  |  |  | 1.742% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0201 | Material Handling | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0202 | Chipping&Padding | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0203 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.8711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0204 | Bolting | KG | 10% | 0.1742% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0205 | Aligenment | KG | 15% | 0.2613% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0206 | Grouting | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0207 | Punch Removing | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0208 | Finall Inspection | KG | 5% | 0.08711% | 40000 | [8 empty] | 40000 | 0 | 40000 | 100% | 0% | 100%
[6 empty] | 1C Radiant Side Wall Panels Axis C+E(Inside) |  |  |  |  | 1.695% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0301 | Material Handling | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0302 | Chipping&Padding | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0303 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.8477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0304 | Bolting | KG | 10% | 0.1695% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0305 | Aligenment | KG | 15% | 0.2543% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0306 | Grouting | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0307 | Punch Removing | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0308 | Finall Inspection | KG | 5% | 0.08477% | 37000 | [8 empty] | 37000 | 0 | 37000 | 100% | 0% | 100%
[6 empty] | 1D Radiant End Wall Panels |  |  |  |  | 0.4198% | 10000 | [8 empty] | 9000 | 0 | 9000 | 86.75% | 0% | 93.25%
[7 empty] | 601.4.1.1.1.0401 | Material Handling |  | 5% | 0.02099% | 10000 | [8 empty] | 9000 | 0 | 9000 | 90% | 0% | 95%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0402 | Installation |  | 50% | 0.2099% | 10000 | [8 empty] | 9000 | 0 | 9000 | 90% | 0% | 95%
[7 empty] | 601.4.1.1.1.0403 | Leveling & Plumbness |  | 15% | 0.06297% | 10000 | [8 empty] | 9000 | 0 | 9000 | 90% | 0% | 95%
[7 empty] | 601.4.1.1.1.0404 | Full Bolt & Tightening |  | 20% | 0.08397% | 10000 | [8 empty] | 8000 | 0 | 8000 | 80% | 0% | 95%
[7 empty] | 601.4.1.1.1.0405 | Touch up |  | 5% | 0.02099% | 10000 | [8 empty] | 7770 | 0 | 7770 | 77.7% | 0% | 77.7%
[7 empty] | 601.4.1.1.1.0406 | Certificate |  | 5% | 0.02099% | 10000 | [8 empty] | 7730 | 0 | 7730 | 77.3% | 0% | 77.3%
[6 empty] | 1E Radiant Roof Panels |  |  |  |  | 0.3654% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0501 | Material Handling |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0502 | Installation |  | 50% | 0.1827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0503 | Leveling & Plumbness |  | 15% | 0.05481% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0504 | Full Bolt & Tightening |  | 20% | 0.07308% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0505 | Touch up |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0506 | Certificate |  | 5% | 0.01827% | 7000 | [8 empty] | 7000 | 0 | 7000 | 100% | 0% | 100%
[6 empty] | 1F Radiant Roof Shadow Box |  |  |  |  | 0.1059% | 2000 | [8 empty] | 2000 | 0 | 2000 | 54.75% | 0% | 54.75%
[7 empty] | 601.4.1.1.1.0601 | Material Handling |  | 5% | 0.005295% | 2000 | [8 empty] | 2000 | 0 | 2000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0602 | Installation |  | 50% | 0.05295% | 2000 | [8 empty] | 1990 | 0 | 1990 | 99.5% | 0% | 99.5%
[7 empty] | 601.4.1.1.1.0603 | Leveling & Plumbness |  | 15% | 0.01588% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.1.0604 | Full Bolt & Tightening |  | 20% | 0.02118% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.1.0605 | Touch up |  | 5% | 0.005295% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.1.0606 | Certificate |  | 5% | 0.005295% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 1G Radiant Transition Roof To Convection |  |  |  |  | 0.2137% | 5000 | [8 empty] | 5000 | 0 | 5000 | 86.06% | 0% | 86.06%
[7 empty] | 601.4.1.1.1.0701 | Material Handling |  | 5% | 0.01069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.1.0702 | Installation |  | 50% | 0.1069% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0703 | Leveling & Plumbness |  | 15% | 0.03206% | 5000 | [8 empty] | 5000 | 0 | 5000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.1.0704 | Full Bolt & Tightening |  | 20% | 0.04274% | 5000 | [8 empty] | 4015 | 0 | 4015 | 80.3% | 0% | 80.3%
[7 empty] | 601.4.1.1.1.0705 | Touch up |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.1.0706 | Certificate |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 02.Radiant Steel Sections | [5 empty] | 4.124% | 102421 | [8 empty] | 102421 | 0 | 102421 | 97.93% | 0% | 98.21%
[6 empty] | 2A1 Columns Steel Structure |  |  |  |  | 1.617% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0101 | Material Handling | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.2.0102 | Installation | KG | 50% | 0.8085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0103 | Leveling & Plumbness | KG | 15% | 0.2425% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0104 | Full Bolt & Tightening | KG | 20% | 0.3234% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0105 | Touch up | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0106 | Certificate | KG | 5% | 0.08085% | 36000 | [8 empty] | 36000 | 0 | 36000 | 100% | 0% | 100%
[6 empty] | 2A2 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0201 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.2.0202 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0203 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0204 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0205 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0206 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A3 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0301 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.2.0302 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0303 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0304 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0305 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0306 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A4 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0401 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.2.0402 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0403 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0404 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0405 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0406 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2A5 Platform |  |  |  |  | 0.3921% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0501 | Material Handling |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.2.0502 | Installation |  | 50% | 0.1961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0503 | Leveling & Plumbness |  | 15% | 0.05881% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0504 | Full Bolt & Tightening |  | 20% | 0.07842% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0505 | Touch up |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0506 | Certificate |  | 5% | 0.01961% | 8000 | [8 empty] | 8000 | 0 | 8000 | 100% | 0% | 100%
[6 empty] | 2B Railing (Handrail) For Radiant Platforms |  |  |  |  | 0.4616% | 7750 | [8 empty] | 7750 | 0 | 7750 | 81.52% | 0% | 84%
[7 empty] | 601.4.1.1.2.0601 | Material Handling |  | 5% | 0.02308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
12.Lader & Handrail | [6 empty] | 601.4.1.1.2.0602 | Installation |  | 50% | 0.2308% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0603 | Leveling & Plumbness |  | 15% | 0.06924% | 7750 | [8 empty] | 7750 | 0 | 7750 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0604 | Full Bolt & Tightening |  | 20% | 0.09232% | 7750 | [8 empty] | 4465 | 0 | 4465 | 57.61% | 0% | 70%
[7 empty] | 601.4.1.1.2.0605 | Touch up |  | 5% | 0.02308% | 7750 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.2.0606 | Certificate |  | 5% | 0.02308% | 7750 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 2C Ladders For Radiant Platforms |  |  |  |  | 0.0605% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0701 | Material Handling |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
12.Lader & Handrail | [6 empty] | 601.4.1.1.2.0702 | Installation |  | 50% | 0.03025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0703 | Leveling & Plumbness |  | 15% | 0.009075% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0704 | Full Bolt & Tightening |  | 20% | 0.0121% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0705 | Touch up |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0706 | Certificate |  | 5% | 0.003025% | 2504 | [8 empty] | 2504 | 0 | 2504 | 100% | 0% | 100%
[6 empty] | 2D Grating For Radiant Platforms |  |  |  |  | 0.417% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0801 | Material Handling | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
13.Grating | [6 empty] | 601.4.1.1.2.0802 | installation | KG | 65% | 0.2711% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0803 | Clamping & Tightening | KG | 20% | 0.0834% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0804 | Touch up & Cleaning | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.2.0805 | Certificate | KG | 5% | 0.02085% | 24167 | [8 empty] | 24167 | 0 | 24167 | 100% | 0% | 100%
[5 empty] | 03.Convection, Header Box Convection Breeching Plate Sections | [5 empty] | 2.522% | 57000 | [8 empty] | 44000 | 0 | 44000 | 77.54% | 0% | 77.54%
[6 empty] | 3A Convection Floor Panels |  |  |  |  | 0.1812% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0101 | Material Handling |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.3.0102 | Installation |  | 50% | 0.09058% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0103 | Leveling & Plumbness |  | 15% | 0.02717% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0104 | Full Bolt & Tightening |  | 20% | 0.03623% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0105 | Touch up |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0106 | Certificate |  | 5% | 0.009057% | 4000 | [8 empty] | 4000 | 0 | 4000 | 100% | 0% | 100%
[6 empty] | 3B Convection Side Wall (Inside) |  |  |  |  | 1.039% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0201 | Material Handling |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.3.0202 | Installation |  | 50% | 0.5197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0203 | Leveling & Plumbness |  | 15% | 0.1559% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0204 | Full Bolt & Tightening |  | 20% | 0.2079% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0205 | Touch up |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0206 | Certificate |  | 5% | 0.05197% | 24000 | [8 empty] | 24000 | 0 | 24000 | 100% | 0% | 100%
[6 empty] | 3C Convection Side Wall (Outside) |  |  |  |  | 0.735% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0301 | Material Handling |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.3.0302 | Installation |  | 50% | 0.3675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0303 | Leveling & Plumbness |  | 15% | 0.1103% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0304 | Full Bolt & Tightening |  | 20% | 0.147% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0305 | Touch up |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.3.0306 | Certificate |  | 5% | 0.03675% | 16000 | [8 empty] | 16000 | 0 | 16000 | 100% | 0% | 100%
[6 empty] | 3D Header box |  |  |  |  | 0.3526% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0401 | Material Handling |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.3.0402 | Installation |  | 50% | 0.1763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0403 | Leveling & Plumbness |  | 15% | 0.05289% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0404 | Full Bolt & Tightening |  | 20% | 0.07052% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0405 | Touch up |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0406 | Certificate |  | 5% | 0.01763% | 8000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3E Convection Breeching |  |  |  |  | 0.2139% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0501 | Material Handling |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.3.0502 | Installation |  | 50% | 0.1069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0503 | Leveling & Plumbness |  | 15% | 0.03208% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0504 | Full Bolt & Tightening |  | 20% | 0.04277% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0505 | Touch up |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.3.0506 | Certificate |  | 5% | 0.01069% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 04.Flue Gas Duct & Stack Plate Section | [5 empty] | 0.09627% | 2510 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3F Flue Gas Duc |  |  |  |  | 0.06198% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0101 | Material Handling |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.4.0102 | Installation |  | 50% | 0.03099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0103 | Leveling & Plumbness |  | 15% | 0.009297% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0104 | Full Bolt & Tightening |  | 20% | 0.0124% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0105 | Touch up |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0106 | Certificate |  | 5% | 0.003099% | 1600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 3G Stack |  |  |  |  | 0.03429% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0201 | Material Handling |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.4.0202 | Installation |  | 50% | 0.01715% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0203 | Leveling & Plumbness |  | 15% | 0.005143% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0204 | Full Bolt & Tightening |  | 20% | 0.006858% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0205 | Touch up |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.4.0206 | Certificate |  | 5% | 0.001714% | 910 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 05.Convection & Upper Steel Section | [5 empty] | 6.113% | 158776.5 | [8 empty] | 156298.45 | 0 | 156298.45 | 89.36% | 0% | 89.48%
[6 empty] | 4A1 Platform |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0101 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.5.0102 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0103 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0104 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0105 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0106 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[6 empty] | 4A2 Columns And Steel Structure |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 86.7% | 0% | 86.7%
[7 empty] | 601.4.1.1.5.0201 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.5.0202 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0203 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 33500 | 0 | 33500 | 79.76% | 0% | 79.76%
[7 empty] | 601.4.1.1.5.0204 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 33200 | 0 | 33200 | 79.05% | 0% | 79.05%
[7 empty] | 601.4.1.1.5.0205 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 33000 | 0 | 33000 | 78.57% | 0% | 78.57%
[7 empty] | 601.4.1.1.5.0206 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 4A3 Columns And Steel Structure |  |  |  |  | 1.803% | 42000 | [8 empty] | 42000 | 0 | 42000 | 85.83% | 0% | 85.83%
[7 empty] | 601.4.1.1.5.0301 | Material Handling |  | 5% | 0.09015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.5.0302 | Installation |  | 50% | 0.9015% | 42000 | [8 empty] | 42000 | 0 | 42000 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0303 | Leveling & Plumbness |  | 15% | 0.2705% | 42000 | [8 empty] | 39900 | 0 | 39900 | 95% | 0% | 95%
[7 empty] | 601.4.1.1.5.0304 | Full Bolt & Tightening |  | 20% | 0.3606% | 42000 | [8 empty] | 34820 | 0 | 34820 | 82.9% | 0% | 82.9%
[7 empty] | 601.4.1.1.5.0305 | Touch up |  | 5% | 0.09015% | 42000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.5.0306 | Certificate |  | 5% | 0.09015% | 42000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 4B Railing (Handrail) For Convection & Upper Section Platforms |  |  |  |  | 0.2157% | 5500 | [8 empty] | 5500 | 0 | 5500 | 72.09% | 0% | 75.5%
[7 empty] | 601.4.1.1.5.0401 | Material Handling |  | 5% | 0.01078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
12.Lader & Handrail | [6 empty] | 601.4.1.1.5.0402 | Installation |  | 50% | 0.1078% | 5500 | [8 empty] | 5500 | 0 | 5500 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0403 | Leveling & Plumbness |  | 15% | 0.03235% | 5500 | [8 empty] | 3300 | 0 | 3300 | 60% | 0% | 70%
[7 empty] | 601.4.1.1.5.0404 | Full Bolt & Tightening |  | 20% | 0.04314% | 5500 | [8 empty] | 2225 | 0 | 2225 | 40.45% | 0% | 50%
[7 empty] | 601.4.1.1.5.0405 | Touch up |  | 5% | 0.01078% | 5500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.5.0406 | Certificate |  | 5% | 0.01078% | 5500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 4C Ladders For Convection & Upper Section Platforms |  |  |  |  | 0.06037% | 2496 | [8 empty] | 2496 | 0 | 2496 | 88.33% | 0% | 88.33%
[7 empty] | 601.4.1.1.5.0501 | Material Handling |  | 5% | 0.003018% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
12.Lader & Handrail | [6 empty] | 601.4.1.1.5.0502 | Installation |  | 50% | 0.03019% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0503 | Leveling & Plumbness |  | 15% | 0.009056% | 2496 | [8 empty] | 2496 | 0 | 2496 | 100% | 0% | 100%
[7 empty] | 601.4.1.1.5.0504 | Full Bolt & Tightening |  | 20% | 0.01207% | 2496 | [8 empty] | 2287 | 0 | 2287 | 91.63% | 0% | 91.63%
[7 empty] | 601.4.1.1.5.0505 | Touch up |  | 5% | 0.003018% | 2496 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.5.0506 | Certificate |  | 5% | 0.003018% | 2496 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 4D Grating For Convection & Upper Section Platforms |  |  |  |  | 0.4276% | 24780.5 | [8 empty] | 22302.45 | 0 | 22302.45 | 79.41% | 0% | 79.41%
[7 empty] | 601.4.1.1.5.0601 | Material Handling | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 22302.45 | 0 | 22302.45 | 90% | 0% | 90%
13.Grating | [6 empty] | 601.4.1.1.5.0602 | installation | KG | 65% | 0.2779% | 24780.5 | [8 empty] | 22302.45 | 0 | 22302.45 | 90% | 0% | 90%
[7 empty] | 601.4.1.1.5.0603 | Clamping & Tightening | KG | 20% | 0.08551% | 24780.5 | [8 empty] | 20330 | 0 | 20330 | 82.04% | 0% | 82.04%
[7 empty] | 601.4.1.1.5.0604 | Touch up & Cleaning | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.5.0605 | Certificate | KG | 5% | 0.02138% | 24780.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 06.Other Accessories | [5 empty] | 2% | 2160 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Peep Doors |  |  |  |  | 1% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.6.0101 | Installation | KG | 50% | 0.5% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.6.0102 | Tightening | KG | 25% | 0.25% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.6.0103 | Certificate | KG | 25% | 0.25% | 1500 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Accessories Doors(Z-1110) |  |  |  |  | 1% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
11.ACTIVITY 1~4 (OLFINE 1) | [6 empty] | 601.4.1.1.6.0201 | Installation | KG | 50% | 0.5% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.6.0202 | Tightening | KG | 25% | 0.25% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.1.6.0203 | Certificate | KG | 25% | 0.25% | 660 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 2.Furnace Coil System | [6 empty] | 4.5% | 189708.2 | [8 empty] | 10074.4569 | 0 | 10074.4569 | 29.33% | 0% | 36.22%
[5 empty] | 07.Radiant Coils & Accessories | [5 empty] | 2% | 40200 | [8 empty] | 22110 | 0 | 22110 | 55% | 0% | 70.5%
[6 empty] | Radiant Coils (Inlet Coil & OutlentCoil) |  |  |  |  | 2% | 40200 | [8 empty] | 22110 | 0 | 22110 | 55% | 0% | 70.5%
[7 empty] | 601.4.1.2.1.0101 | Material Handling | KG | 5% | 0.1% | 40200 | [8 empty] | 40200 | 0 | 40200 | 100% | 0% | 100%
15.Furnace Coil System | [6 empty] | 601.4.1.2.1.0102 | Erection | KG | 50% | 1% | 40200 | [8 empty] | 40200 | 0 | 40200 | 100% | 0% | 100%
[7 empty] | 601.4.1.2.1.0103 | Aligenment/Leveling | KG | 20% | 0.4% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 70%
[7 empty] | 601.4.1.2.1.0104 | Full Bolting/Welding | KG | 15% | 0.3% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 10%
[7 empty] | 601.4.1.2.1.0106 | Punch Removing | KG | 5% | 0.1% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.1.0107 | Certificate | KG | 5% | 0.1% | 40200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 08.Convection Coils & Accessories | [5 empty] | 1.7% | 144440.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Economiser (ECO) |  |  |  |  | 0.2% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0101 | Material Handling | NO. | 10% | 0.02% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0102 | Installation | NO. | 60% | 0.12% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0103 | Fixing & tightening | NO. | 15% | 0.03% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0104 | Setting & Alignment | NO. | 10% | 0.02% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0105 | Certificate | NO. | 5% | 0.01% | 22680 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Feed Preheater (FPH) |  |  |  |  | 0.21% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0201 | Material Handling | NO. | 10% | 0.021% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0202 | Installation | NO. | 60% | 0.126% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0203 | Fixing & tightening | NO. | 15% | 0.0315% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0204 | Setting & Alignment | NO. | 10% | 0.021% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0205 | Certificate | NO. | 5% | 0.0105% | 36260 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Pressure Steam Superheater One (HPSSH-I) |  |  |  |  | 0.1% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0301 | Material Handling | NO. | 10% | 0.01% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0302 | Installation | NO. | 60% | 0.06% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0303 | Fixing & tightening | NO. | 15% | 0.015% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0304 | Setting & Alignment | NO. | 10% | 0.01% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0305 | Certificate | NO. | 5% | 0.005% | 9550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Pressure Steam Superheater One (HPSSH-II) |  |  |  |  | 0.09% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0401 | Material Handling | NO. | 10% | 0.009% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0402 | Installation | NO. | 60% | 0.054% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0403 | Fixing & tightening | NO. | 15% | 0.0135% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0404 | Setting & Alignment | NO. | 10% | 0.009% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0405 | Certificate | NO. | 5% | 0.0045% | 7000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Temperature Coil One (HTC-I) |  |  |  |  | 0.25% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0501 | Material Handling | NO. | 10% | 0.025% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0502 | Installation | NO. | 60% | 0.15% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0503 | Fixing & tightening | NO. | 15% | 0.0375% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0504 | Setting & Alignment | NO. | 10% | 0.025% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0505 | Certificate | NO. | 5% | 0.0125% | 26550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | High Temperature Coil One (HTC-II) |  |  |  |  | 0.2% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0601 | Material Handling | NO. | 10% | 0.02% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0602 | Installation | NO. | 60% | 0.12% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0603 | Fixing & tightening | NO. | 15% | 0.03% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0604 | Setting & Alignment | NO. | 10% | 0.02% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0605 | Certificate | NO. | 5% | 0.01% | 20120 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | HT Crossover (HTX) |  |  |  |  | 0.09% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0701 | Material Handling | NO. | 10% | 0.009% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0702 | Installation | NO. | 60% | 0.054% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0703 | Fixing & tightening | NO. | 15% | 0.0135% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0704 | Setting & Alignment | NO. | 10% | 0.009% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0705 | Certificate | NO. | 5% | 0.0045% | 2100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | LT Crossover B(LTX-B) |  |  |  |  | 0.09% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0801 | Material Handling | NO. | 10% | 0.009% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0802 | Installation | NO. | 60% | 0.054% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0803 | Fixing & tightening | NO. | 15% | 0.0135% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0804 | Setting & Alignment | NO. | 10% | 0.009% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0805 | Certificate | NO. | 5% | 0.0045% | 2000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | LT Crossover T(LTX-T) |  |  |  |  | 0.06% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0901 | Material Handling | NO. | 10% | 0.006% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.0902 | Installation | NO. | 60% | 0.036% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0903 | Fixing & tightening | NO. | 15% | 0.009% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0904 | Setting & Alignment | NO. | 10% | 0.006% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.0905 | Certificate | NO. | 5% | 0.003% | 1000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Venture For X-Over System |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1001 | Material Handling | NO. | 10% | 0.01% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.1002 | Installation | NO. | 60% | 0.06% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1003 | Fixing & tightening | NO. | 15% | 0.015% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1004 | Setting & Alignment | NO. | 10% | 0.01% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1005 | Certificate | NO. | 5% | 0.005% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Comsockets |  |  |  |  | 0.08% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1101 | Material Handling | NO. | 10% | 0.008% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.1102 | Installation | NO. | 60% | 0.048% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1103 | Fixing & tightening | NO. | 15% | 0.012% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1104 | Setting & Alignment | NO. | 10% | 0.008% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1105 | Certificate | NO. | 5% | 0.004% | 1789.2 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Brackets |  |  |  |  | 0.15% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1201 | Material Handling | NO. | 10% | 0.015% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.1202 | Installation | NO. | 60% | 0.09% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1203 | Fixing & tightening | NO. | 15% | 0.0225% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1204 | Setting & Alignment | NO. | 10% | 0.015% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1205 | Certificate | NO. | 5% | 0.0075% | 13550 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Common Part |  |  |  |  | 0.08% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1301 | Material Handling | NO. | 10% | 0.008% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
15.Furnace Coil System | [6 empty] | 601.4.1.2.2.1302 | Installation | NO. | 60% | 0.048% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1303 | Fixing & tightening | NO. | 15% | 0.012% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1304 | Setting & Alignment | NO. | 10% | 0.008% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.2.1305 | Certificate | NO. | 5% | 0.004% | 1840 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 09.Spring Support | [5 empty] | 0.8% | 5068 | [8 empty] | 1393.82 | 0 | 1393.82 | 27.5% | 0% | 27.5%
[6 empty] | Content Spring Support & HangerTie-Roads |  |  |  |  | 0.8% | 5068 | [8 empty] | 1393.82 | 0 | 1393.82 | 27.5% | 0% | 27.5%
[7 empty] | 601.4.1.2.3.0101 | Material Handling |  | 5% | 0.04% | 5068 | [8 empty] | 2027.2 | 0 | 2027.2 | 40% | 0% | 40%
16.Spring Support | [6 empty] | 601.4.1.2.3.0102 | Erection |  | 55% | 0.44% | 5068 | [8 empty] | 2027.2 | 0 | 2027.2 | 40% | 0% | 40%
[7 empty] | 601.4.1.2.3.0103 | Fixing & tightening |  | 25% | 0.2% | 5068 | [8 empty] | 710 | 0 | 710 | 14.01% | 0% | 14.01%
[7 empty] | 601.4.1.2.3.0104 | Punch Removing |  | 10% | 0.08% | 5068 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.2.3.0105 | Certificate |  | 5% | 0.04% | 5068 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 3.Furnace Equipment | [6 empty] | 5.5% | 230164.2 | [8 empty] | 117856.301 | 0 | 117856.301 | 45.15% | 0% | 45.15%
[5 empty] | 10.FIX Equipment | [5 empty] | 5.5% | 230164.2 | [8 empty] | 117856.301 | 0 | 117856.301 | 45.15% | 0% | 45.15%
[6 empty] | Bottom Burners (F1110) |  |  |  |  | 0.45% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0101 | Material Handling | NO. | 10% | 0.045% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0102 | Installation | NO. | 60% | 0.27% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0103 | Fixing & tightening | NO. | 15% | 0.0675% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0104 | Setting & Alignment | NO. | 10% | 0.045% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0105 | Certificate | NO. | 5% | 0.0225% | 10128.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Side Wall Burners( F1111) |  |  |  |  | 0.45% | 14628.6 | [8 empty] | 512.001 | 0 | 512.001 | 3.5% | 0% | 3.5%
[7 empty] | 601.4.1.3.1.0201 | Material Handling | NO. | 10% | 0.045% | 14628.6 | [8 empty] | 731.43 | 0 | 731.43 | 5% | 0% | 5%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0202 | Installation | NO. | 60% | 0.27% | 14628.6 | [8 empty] | 731.43 | 0 | 731.43 | 5% | 0% | 5%
[7 empty] | 601.4.1.3.1.0203 | Fixing & tightening | NO. | 15% | 0.0675% | 14628.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0204 | Setting & Alignment | NO. | 10% | 0.045% | 14628.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0205 | Certificate | NO. | 5% | 0.0225% | 14628.6 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Primery TLE (E-110 A) |  |  |  |  | 0.49% | 17100 | [8 empty] | 14745.5 | 0 | 14745.5 | 86.23% | 0% | 86.23%
[7 empty] | 601.4.1.3.1.0301 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0302 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0303 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0304 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0305 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 4210 | 0 | 4210 | 24.62% | 0% | 24.62%
[6 empty] | Primery TLE (E-110 B) |  |  |  |  | 0.49% | 17100 | [8 empty] | 14750 | 0 | 14750 | 86.26% | 0% | 86.26%
[7 empty] | 601.4.1.3.1.0401 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0402 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0403 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0404 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0405 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 4300 | 0 | 4300 | 25.15% | 0% | 25.15%
[6 empty] | Primery TLE (E-110 C) |  |  |  |  | 0.49% | 17100 | [8 empty] | 14745.5 | 0 | 14745.5 | 86.23% | 0% | 86.23%
[7 empty] | 601.4.1.3.1.0501 | Material Handling | NO. | 10% | 0.049% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0502 | Installation | NO. | 60% | 0.294% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0503 | Fixing & tightening | NO. | 15% | 0.0735% | 17100 | [8 empty] | 17100 | 0 | 17100 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0504 | Setting & Alignment | NO. | 10% | 0.049% | 17100 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0505 | Certificate | NO. | 5% | 0.0245% | 17100 | [8 empty] | 4210 | 0 | 4210 | 24.62% | 0% | 24.62%
[6 empty] | Secondary TLE (E-1120) |  |  |  |  | 0.6% | 35200 | [8 empty] | 29327.5 | 0 | 29327.5 | 83.32% | 0% | 83.32%
[7 empty] | 601.4.1.3.1.0601 | Material Handling | NO. | 10% | 0.06% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0602 | Installation | NO. | 60% | 0.36% | 35200 | [8 empty] | 35200 | 0 | 35200 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0603 | Fixing & tightening | NO. | 15% | 0.09% | 35200 | [8 empty] | 31250 | 0 | 31250 | 88.78% | 0% | 88.78%
[7 empty] | 601.4.1.3.1.0604 | Setting & Alignment | NO. | 10% | 0.06% | 35200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0605 | Certificate | NO. | 5% | 0.03% | 35200 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Tertiary TLE (E-1130) |  |  |  |  | 0.8% | 50030 | [8 empty] | 43775.8 | 0 | 43775.8 | 87.5% | 0% | 87.5%
[7 empty] | 601.4.1.3.1.0701 | Material Handling | NO. | 10% | 0.08% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0702 | Installation | NO. | 60% | 0.48% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0703 | Fixing & tightening | NO. | 15% | 0.12% | 50030 | [8 empty] | 50030 | 0 | 50030 | 100% | 0% | 100%
[7 empty] | 601.4.1.3.1.0704 | Setting & Alignment | NO. | 10% | 0.08% | 50030 | [8 empty] | 12503 | 0 | 12503 | 24.99% | 0% | 24.99%
[7 empty] | 601.4.1.3.1.0705 | Certificate | NO. | 5% | 0.04% | 50030 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Decocke Drum (D-11110)B |  |  |  |  | 0.28% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0801 | Material Handling | NO. | 10% | 0.028% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0802 | Installation | NO. | 60% | 0.168% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0803 | Fixing & tightening | NO. | 15% | 0.042% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0804 | Setting & Alignment | NO. | 10% | 0.028% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0805 | Certificate | NO. | 5% | 0.014% | 10700 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | VHPS Steam Drum (D-1110) |  |  |  |  | 0.6% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0901 | Material Handling | NO. | 10% | 0.06% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.0902 | Installation | NO. | 60% | 0.36% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0903 | Fixing & tightening | NO. | 15% | 0.09% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0904 | Setting & Alignment | NO. | 10% | 0.06% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.0905 | Certificate | NO. | 5% | 0.03% | 36000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | VHPS Steam Silencer (X-1110) |  |  |  |  | 0.2% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1001 | Material Handling | NO. | 10% | 0.02% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.1002 | Installation | NO. | 60% | 0.12% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1003 | Fixing & tightening | NO. | 15% | 0.03% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1004 | Setting & Alignment | NO. | 10% | 0.02% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1005 | Certificate | NO. | 5% | 0.01% | 1900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Decocke Air Silencer (X-1120) |  |  |  |  | 0.25% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1101 | Material Handling | NO. | 10% | 0.025% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.1102 | Installation | NO. | 60% | 0.15% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1103 | Fixing & tightening | NO. | 15% | 0.0375% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1104 | Setting & Alignment | NO. | 10% | 0.025% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1105 | Certificate | NO. | 5% | 0.0125% | 6000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Induct Draft Fan (C-1110 & M1110) |  |  |  |  | 0.4% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1201 | Material Handling | NO. | 10% | 0.04% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
17.Fix Equipment | [6 empty] | 601.4.1.3.1.1202 | Installation | NO. | 60% | 0.24% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1203 | Fixing & tightening | NO. | 15% | 0.06% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1204 | Setting & Alignment | NO. | 10% | 0.04% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.3.1.1205 | Certificate | NO. | 5% | 0.02% | 14277 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 4.Refractory Lining & Insulating Firebricks | [6 empty] | 11.82% | 333983.55 | [8 empty] | 307144.16 | 0 | 68597.1598 | 74.13% | 0% | 74.89%
[5 empty] | 11.Refractory Lining & Insulating Firebricks | [5 empty] | 11.82% | 333983.55 | [8 empty] | 307144.16 | 0 | 68597.1598 | 74.13% | 0% | 74.89%
[6 empty] | Radiant Floor |  |  |  |  | 1% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0101 | Material Handling |  | 10% | 0.1% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0102 | Preparatoin |  | 5% | 0.05% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0103 | Installation |  | 60% | 0.6% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0104 | Completion Work |  | 15% | 0.15% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0105 | Punch Removing & Cleaning |  | 5% | 0.05% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0106 | Certificate |  | 5% | 0.05% | 20576 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Radiant Side Wall And South End Wall |  |  |  |  | 3.515% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0201 | Material Handling |  | 10% | 0.3515% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0202 | Preparatoin |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0203 | Installation |  | 60% | 2.109% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0204 | Completion Work |  | 15% | 0.5272% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0205 | Punch Removing & Cleaning |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0206 | Certificate |  | 5% | 0.1757% | 202745.25 | [8 empty] | 202745.25 | 0 | 202745.25 | 100% | 0% | 100%
[6 empty] | Radiant North End Wall |  |  |  |  | 0.6% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 75% | 0% | 90%
[7 empty] | 601.4.1.4.1.0301 | Material Handling |  | 10% | 0.06% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0302 | Preparatoin |  | 5% | 0.03% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0303 | Installation |  | 60% | 0.36% | 20385.38 | [8 empty] | 20385.38 | 0 | 20385.38 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0304 | Completion Work |  | 15% | 0.09% | 20385.38 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 100%
[7 empty] | 601.4.1.4.1.0305 | Punch Removing & Cleaning |  | 5% | 0.03% | 20385.38 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0306 | Certificate |  | 5% | 0.03% | 20385.38 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Radiant Roof And shadow Box |  |  |  |  | 0.35% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 75% | 0% | 75%
[7 empty] | 601.4.1.4.1.0401 | Material Handling |  | 10% | 0.035% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0402 | Preparatoin |  | 5% | 0.0175% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0403 | Installation |  | 60% | 0.21% | 4958.25 | [8 empty] | 4958.25 | 0 | 4958.25 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0404 | Completion Work |  | 15% | 0.0525% | 4958.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0405 | Punch Removing & Cleaning |  | 5% | 0.0175% | 4958.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0406 | Certificate |  | 5% | 0.0175% | 4958.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Cross Over Floor |  |  |  |  | 0.5% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0501 | Material Handling |  | 10% | 0.05% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0502 | Preparatoin |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0503 | Installation |  | 60% | 0.3% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0504 | Completion Work |  | 15% | 0.075% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0505 | Punch Removing & Cleaning |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0506 | Certificate |  | 5% | 0.025% | 18896 | [8 empty] | 18896 | 0 | 18896 | 100% | 0% | 100%
[6 empty] | Cross Over Side Wall And South End Wall |  |  |  |  | 1.22% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0601 | Material Handling |  | 10% | 0.122% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0602 | Preparatoin |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0603 | Installation |  | 60% | 0.732% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0604 | Completion Work |  | 15% | 0.183% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0605 | Punch Removing & Cleaning |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0606 | Certificate |  | 5% | 0.061% | 17435.95 | [8 empty] | 17435.95 | 0 | 17435.95 | 100% | 0% | 100%
[6 empty] | Cross Over Roof |  |  |  |  | 0.8% | 11450 | [8 empty] | 11450 | 0 | 11450 | 60.07% | 0% | 60.07%
[7 empty] | 601.4.1.4.1.0701 | Material Handling |  | 10% | 0.08% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0702 | Preparatoin |  | 5% | 0.04% | 11450 | [8 empty] | 11450 | 0 | 11450 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0703 | Installation |  | 60% | 0.48% | 11450 | [8 empty] | 8600 | 0 | 8600 | 75.11% | 0% | 75.11%
[7 empty] | 601.4.1.4.1.0704 | Completion Work |  | 15% | 0.12% | 11450 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0705 | Punch Removing & Cleaning |  | 5% | 0.04% | 11450 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0706 | Certificate |  | 5% | 0.04% | 11450 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Convection Side Wall |  |  |  |  | 1.5% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0801 | Material Handling |  | 10% | 0.15% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0802 | Preparatoin |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0803 | Installation |  | 60% | 0.9% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0804 | Completion Work |  | 15% | 0.225% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0805 | Punch Removing & Cleaning |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.0806 | Certificate |  | 5% | 0.075% | 26899.33 | [8 empty] | 26899.33 | 0 | 26899.33 | 100% | 0% | 100%
[6 empty] | Header Box |  |  |  |  | 1% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0901 | Material Handling |  | 10% | 0.1% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0902 | Preparatoin |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.0903 | Installation |  | 60% | 0.6% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0904 | Completion Work |  | 15% | 0.15% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0905 | Punch Removing & Cleaning |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.0906 | Certificate |  | 5% | 0.05% | 1220.14 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | breeching |  |  |  |  | 0.83% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.1001 | Material Handling |  | 10% | 0.083% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.1002 | Preparatoin |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.1003 | Installation |  | 60% | 0.498% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.1004 | Completion Work |  | 15% | 0.1245% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.1005 | Punch Removing & Cleaning |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[7 empty] | 601.4.1.4.1.1006 | Certificate |  | 5% | 0.0415% | 4374 | [8 empty] | 4374 | 0 | 4374 | 100% | 0% | 100%
[6 empty] | Shadow Box |  |  |  |  | 0.5% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.1101 | Material Handling |  | 10% | 0.05% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.1102 | Preparatoin |  | 5% | 0.025% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
18.Refractory Lining & Insulating Firebricks | [6 empty] | 601.4.1.4.1.1103 | Installation |  | 60% | 0.3% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.1104 | Completion Work |  | 15% | 0.075% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.1105 | Punch Removing & Cleaning |  | 5% | 0.025% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.4.1.1106 | Certificate |  | 5% | 0.025% | 5043.25 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 5.Protrusion Seals | [6 empty] | 1.25% | 134 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 12.Protrusion Seals | [5 empty] | 1.25% | 134 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Multi Tube Bellow (End Location) |  |  |  |  | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0101 | Completion Work | - | 100% | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Multi Tube Bellow (Intermediate Location) |  |  |  |  | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0201 | Completion Work | - | 100% | 0.25% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Spring Joint (Hanger Tube Through Arch ) |  |  |  |  | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0301 | Completion Work | - | 100% | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Spring Joint (Guide Tube Through Floor ) |  |  |  |  | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0401 | Completion Work | - | 100% | 0.2% | 18 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | CRF Rope (Outlet Tube) |  |  |  |  | 0.25% | 96 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0501 | Completion Work | - | 100% | 0.25% | 96 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Certification |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.1.5.1.0601 | Completion Work | - | 100% | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 2.PipeRack A1 (OLFINE 2) | [7 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 4.125%
|  |  |  | 6.PipeRack A1 (OLFINE 2) | [6 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 4.125%
[5 empty] | 13.PipeRack A1 (OLFINE 2) | [5 empty] | 2% | 80000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 4.125%
[6 empty] | 5A+5C Stair House |  |  |  |  | 1.5% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 5.5%
[7 empty] | 601.4.2.1.1.0101 | Material Handling | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 10%
[7 empty] | 601.4.2.1.1.0102 | Chipping&Padding | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 100%
14.PipeRack A1 (OLFINE 1) | [6 empty] | 601.4.2.1.1.0103 | Installation(Column/Beam/Bracing/Stair) | KG | 50% | 0.75% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0104 | Bolting | KG | 10% | 0.15% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0105 | Aligenment | KG | 15% | 0.225% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0106 | Grouting | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0107 | Punch Removing | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0108 | Finall Inspection | KG | 5% | 0.075% | 72000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 5B+5D Handrial Stair |  |  |  |  | 0.25% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0201 | Material Handling |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
14.PipeRack A1 (OLFINE 1) | [6 empty] | 601.4.2.1.1.0202 | Installation |  | 50% | 0.125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0203 | Leveling & Plumbness |  | 15% | 0.0375% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0204 | Full Bolt & Tightening |  | 20% | 0.05% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0205 | Touch up |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0206 | Certificate |  | 5% | 0.0125% | 3000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | 5B+5D Handrial Stair |  |  |  |  | 0.25% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0301 | Material Handling | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
14.PipeRack A1 (OLFINE 1) | [6 empty] | 601.4.2.1.1.0302 | installation | KG | 65% | 0.1625% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0303 | Clamping & Tightening | KG | 20% | 0.05% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0304 | Touch up & Cleaning | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.2.1.1.0305 | Certificate | KG | 5% | 0.0125% | 5000 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 3.Inlet & Outlet Piping | [7 empty] | 3% | 1800 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 7.Piping From Inlet Header To Furnace | [6 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 14.grinding & Fitup & Welding | [5 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Workshop |  |  |  |  | 0.5% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0101 | Material Handling | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
19.Inlet & Outlet Piping | [6 empty] | 601.4.3.1.1.0102 | Fitup | KG | 30% | 0.15% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
20.Inlet & Outlet Piping | [6 empty] | 601.4.3.1.1.0103 | Welding | KG | 35% | 0.175% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0104 | NDT & PWHT | KG | 15% | 0.075% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0106 | Reinstatement | KG | 10% | 0.05% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0107 | Certificate | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Location |  |  |  |  | 1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0201 | Material Handling | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
19.Inlet & Outlet Piping | [6 empty] | 601.4.3.1.1.0202 | Fitup | KG | 30% | 0.3% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
20.Inlet & Outlet Piping | [6 empty] | 601.4.3.1.1.0203 | Welding | KG | 35% | 0.35% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0204 | NDT & PWHT | KG | 15% | 0.15% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0206 | Reinstatement | KG | 10% | 0.1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.1.1.0207 | Certificate | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 8.Piping From Inlet Header To Furnace | [6 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 15.grinding & Fitup & Welding | [5 empty] | 1.5% | 900 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Workshop |  |  |  |  | 0.5% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0101 | Material Handling | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
19.Inlet & Outlet Piping | [6 empty] | 601.4.3.2.1.0102 | Fitup | KG | 30% | 0.15% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
20.Inlet & Outlet Piping | [6 empty] | 601.4.3.2.1.0103 | Welding | KG | 35% | 0.175% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0104 | NDT & PWHT | KG | 15% | 0.075% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0106 | Reinstatement | KG | 10% | 0.05% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0107 | Certificate | KG | 5% | 0.025% | 300 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | grinding & Fitup & Welding in Location |  |  |  |  | 1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0201 | Material Handling | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
19.Inlet & Outlet Piping | [6 empty] | 601.4.3.2.1.0202 | Fitup | KG | 30% | 0.3% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
20.Inlet & Outlet Piping | [6 empty] | 601.4.3.2.1.0203 | Welding | KG | 35% | 0.35% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0204 | NDT & PWHT | KG | 15% | 0.15% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0206 | Reinstatement | KG | 10% | 0.1% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.3.2.1.0207 | Certificate | KG | 5% | 0.05% | 600 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 4.Delivery of MC Book | [7 empty] | 0.75% | 5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 9.F-110 | [6 empty] | 0.695% | 4.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 16.Furnace & Refractory | [5 empty] | 0.695% | 4.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Steel Structure (Plate & Steel) |  |  |  |  | 0.245% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.1.1.0101 | Completion Work | - | 100% | 0.245% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Coil System |  |  |  |  | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.1.1.0201 | Completion Work | - | 100% | 0.1% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Furnace Coil Equipment |  |  |  |  | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.1.1.0301 | Completion Work | - | 100% | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Refractory Lining & Insulating Firebricks |  |  |  |  | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.1.1.0401 | Completion Work | - | 100% | 0.15% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Protrusion Seals |  |  |  |  | 0.05% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.1.1.0501 | Completion Work | - | 100% | 0.05% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 9.PipeRack A1 (OLFINE 2) | [6 empty] | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 17.Stair House For F-111 | [5 empty] | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Stair House For F-112 |  |  |  |  | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.4.4.2.1.0101 | Completion Work | - | 100% | 0.055% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  | 5.Demobilization | [8 empty] | 1.87% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  | 5.Demobilization | [7 empty] | 1.87% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  |  |  | 1.Demobilization | [6 empty] | 1.87% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[5 empty] | 18.Demobilization | [5 empty] | 1.87% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[6 empty] | Demobilization project |  |  |  |  | 1.87% | 1 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.5.1.1.1.01.01 | Demobilization (OLF1) |  | 50% | 0.935% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
[7 empty] | 601.5.1.1.1.01.02 | Demobilization (OLF2) |  | 50% | 0.935% | 0.5 | [8 empty] | 0 | 0 | 0 | 0% | 0% | 0%
|  | 6.Finish | [8 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%
|  |  | 6.Finish | [7 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%
|  |  |  | 1.Finish | [6 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%
[5 empty] | 19.Finish | [5 empty] | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%
[6 empty] | Finish (OLF1& OLFF2) |  |  |  |  | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%
[7 empty] | 601.6.1.1.1.01.01 | Finish (OLF1& OLFF2) |  | 100% | 0% | 0 | [8 empty] | 0 | 0 | 0 | 0% | 100% | 0%